## Sheet1
Risk No. | Risk Description | Risk Resolution Measures | Justification
R1 | Inaccurate estimation | Update the estimation as the project progresses as new details emerge | Agile estimation methods are not accurate. They only provide a good enough estimation.
R2 | Poor end-user engagement | Perform user testing surveys, release software versions frequently for user testing, and perform beta testing before the final product release. | Poor end-user engagement could cause the end user to decline to use the software product as intended. In this case, students or career advisors would fail to use SAMS as anticipated, hampering the project's success.
R3 | Poor quality code | Establish clear coding standards, perform code reviews, and test all code. Also, hire seasoned programmers who understand the tenets of computer science. | Poor quality code increases the chances of failure of a software project
R4 | Inadequate risk management | Identify as many risks as possible and prioritize the using the appropriate tools such as a risk register and risk matrix. This helps develop mitigation strategies for risks beforehand. | When a project encounters risks that were not anticipated, a lot of valuable time and resources is wasted trying to develop mitigation strategies. Sometimes the available resources may not be adequate. This increases the chances of a software project not succeeding.
R5 | Inadequate computer science capabilities | Conduct technical analysis and SWOT analysis to allocate tasks more effectively and understand technical shortfalls | Technical analysis and SWOT analysis helps to determine the team strengths and weaknesses.